## TeamF
The Quarantwenties
| Contact Info |  | Introduction |  |  |  |  | Tic-Tac-Toe Game | [5 empty] | Legos | Sprint 1 | [5 empty] | Sprint 2 | [5 empty] | Sprint 3 | [6 empty] | Sprint 4
Name | Email | Phone number | 2020-08-23 | 2020-08-24 | 2020-08-25 | 2020-08-30 | 2020-08-31 | 2020-09-01 | 2020-09-06 | 2020-09-07 | 2020-09-08 | 2020-09-13 | 2020-09-14 | 2020-09-15 | 2020-09-20 | 2020-09-21 | 2020-09-22 | 2020-09-27 | 2020-09-28 | 2020-09-29 | 2020-10-04 | 2020-10-05 | 2020-10-06 | 2020-10-11 | 2020-10-12 | 2020-10-13 | 2020-10-18 | 2020-10-19 | 2020-10-20 | 2020-10-25 | 2020-10-26 | 2020-10-27 | 2020-11-01 | 2020-11-02 | 2020-11-03 | 2020-11-08 | 2020-11-09 | 2020-11-10 | 2020-11-15
Chariane Nkengfack | cnkeng@student.fdu.edu | 908-305-0615 | bar: 2020-08-23 to 2020-09-06
Robert Vargas | r_vargas@student.fdu.edu | 908-405-0762 | bar: 2020-08-23 to 2020-09-06
Ever Nolasco | 1nolasco@student.fdu.edu | 908-220-2437 | bar: 2020-08-23 to 2020-09-06
Christina Schembri | cls18@student.fdu.edu | 347-510-1975 | 2020-08-23: x; 2020-08-24: Work; 2020-08-25: x; 2020-08-31: x; 2020-09-01: x; 2020-09-06: x
Michael DelSignore | mdel@student.fdu.edu | 973-413-4172 | bar: 2020-08-23 to 2020-09-06
Michael Elijius | elijiusm@student.fdu.edu | 862-223-1374 | bar: 2020-08-23 to 2020-09-06
Dominic Rzepecki | domrzep@student.fdu.edu | 973-407-0178 | 2020-08-23: x; 2020-08-24: Work; 2020-08-25: x; 2020-08-30: x; 2020-08-31: Work; 2020-09-01: x; 2020-09-06: x
Objectives/Agenda |  |  | 2020-08-23: Discuss team roles and the adjustments that will be made to them.; 2020-08-24: N/A; 2020-08-25: Make sure everyone has access to the Jira board, complete some of the homework as a group, and answer any questions the team may have.; 2020-08-30: Have everyone contribute to Jira project to show they have access to the Boards; 2020-08-31: Repeat of yesterday's meeting for those who couldn't attend; 2020-09-01: Discuss Tic-Tac-Toe game: planning, roles, timeline
Meeting details/notes |  |  | 2020-08-23: Chariane mentioned that she's going to have to move around the team roles based on Prof. Vallone's helpful suggestions. She also wanted to ensure that her teammates were satisfied with their role assignments. Michael E brought up a great point of asking the team to clarify what each role meant and what their responsibilities & expectations encompassed. This question will be re-addressed during class tomorrow (08/25) to Prof. Vallone for further clarification.; 2020-08-24: Chariane made sure everyone was comfortable with the new team role assignments. Short meeting.; 2020-08-25: Discussed team norms, accessed team project on Jira, and organized team retrospective presentation slide.; 2020-08-30: Everyone agreed to learn Git and also make some edits/comments/issues in the Jira project to show that they have access to it; 2020-08-31: Everyone agreed to learn Git and also make some edits/comments/issues in the Jira project to show that they have access to it; 2020-09-01: We discussed how everyone's roles will affect the production, planning, and execution of this game, and we also created a timeline for when we should expect certain components to be done.
Action Items |  |  | 2020-08-23: Readdress definition of team roles during class; 2020-08-24: N/A; 2020-08-25: Chariane will finish the assigned homework items and submit them on Jira.; 2020-08-30: Everyone is going to make a comment or create an issue to show that they have access to the Jira project, if they haven't done so already; 2020-08-31: N/A; 2020-09-01: Chariane and Christina will work on Tools doc, Dominic will create living doc for Requirements, Ever and Michael E. will code, and Michael D. and Rob will test the program.
Meeting length (in minutes) |  |  | 2020-08-23: 15; 2020-08-24: 3; 2020-08-25: 30; 2020-08-30: 5; 2020-08-31: 5; 2020-09-01: 28m
Key:
scrum meetings
missing
couldn't attened but told the team and sent a progress update